## Gantt Chart
PROJECT PLANNER
PROJECT TITLE |  | Re:Book |  |  |  |  | COMPANY NAME | [6 empty] | Group 5
PROJECT MANAGER |  | Le Thi Kim My |  |  |  |  | DATE | [6 empty] | 2021-10-22
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | PA1
1.1 | Project Plan | bar: WEEK 1 F to WEEK 2 T
1.1.1 | Project Overview | Khôi | 2021-10-22 | 2021-10-22 | 0 | 100% | bar: WEEK 2 W
1.1.2 | Project Organization | Ngân | 2021-10-22 | 2021-10-22 | 0 | 100% | bar: WEEK 2 W to WEEK 3 W
1.1.3 | Phase Plan | Ngân | 2021-10-22 | 2021-10-26 | 4 | 100% | bar: WEEK 2 R to WEEK 3 R
1.1.4 | Project Monitoring | Khôi | 2021-10-22 | 2021-10-26 | 4 | 100% | bar: WEEK 3 M to WEEK 3 R
1.2 | Vision Document | bar: WEEK 3 T to WEEK 3 R
1.2.1 | Positioning | Khôi | 2021-10-26 | 2021-10-29 | 3 | 100% | bar: WEEK 3 F
1.2.2 | Stakeholder and User Descriptions | Thư | 2021-10-26 | 2021-10-29 | 3 | 100% | bar: WEEK 2 W to WEEK 3 W
1.2.3 | Product Overview | Thư | 2021-10-26 | 2021-10-29 | 3 | 100% | bar: WEEK 2 R to WEEK 3 R
1.2.4 | Product Features | Mỹ | 2021-10-26 | 2021-10-29 | 3 | 100% | bar: WEEK 3 M to WEEK 3 R
1.2.5 | Non-functional Requirements | Định | 2021-10-26 | 2021-10-29 | 3 | 100% | bar: WEEK 3 F
1.3 | Weekly Report | Định | 2021-10-22 | 2021-10-29 | 7 | 100% | bar: WEEK 2 W to WEEK 3 W
2 | PA2
2.1 | Revise Project Plan | Khôi | 2021-10-26 | 2021-11-12 | 16 | 100% | bar: WEEK 4 M to WEEK 4 R
2.2 | Detail Vision Document | Ngân | 2021-10-26 | 2021-11-12 | 16 | 100% | bar: WEEK 4 F to WEEK 5 F
2.3 | Use-case Specification Document |  | 2021-10-26 | 2021-11-12 | 16 | 100%
2.3.1 | Use-case Model | Mỹ | 2021-10-26 | 2021-11-12 | 16 | 100%
2.3.2 | Use-case Specifications | All | 2021-10-26 | 2021-11-12 | 16 | 100%
2.4 | Implement |  | 2021-10-26 | 2021-11-12 | 16 | 100%
2.4.1 | Complete UI of Menu, Menu2 | Định | 2021-10-26 | 2021-11-12 | 16 | 100%
2.4.2 | Sign In, Profile display (3rd version) | Mỹ | 2021-10-26 | 2021-11-12 | 16 | 100%
2.4.3 | Take information from Firebase to Profile | Ngân | 2021-10-26 | 2021-11-12 | 16 | 100%
2.4.4 | Do front-end of Sign In by social accounts and register | Khôi | 2021-10-26 | 2021-11-12 | 16 | 100%
2.5 | Weekly Report | Thư | 2021-10-26 | 2021-11-12 | 16 | 100%
3 | PA3
3.1 | Revise Use-case Specification Document |  |  |  | 0 | 0%
3.2 | Software Architecture |  |  |  | 0 | 0%
3.2.1 | Architectural Goals and Constraints |  |  |  | 0 | 0%
3.2.2 | Components & Relationships |  |  |  | 0 | 0%
3.2.2.1 | Draw and Explain Class Diagrams |  |  |  | 0 | 0%
3.3 | Weekly Report |  |  |  | 0 | 0%
4 | PA4
4.1 | Revise Software Architecture |  |  |  | 0 | 0%
4.1.1 | Deployment Diagram |  |  |  | 0 | 0%
4.1.2 | Folder Structure |  |  |  | 0 | 0%
4.2 | Design UI |  |  |  | 0 | 0%
4.3 | Weekly Report |  |  |  | 0 | 0%
5 | PA5
4.1 | Test Plan Document |  |  |  | 0 | 0%
4.1.1 | List Target Test Items |  |  |  | 0 | 0%
4.1.2 | Set Up Testing Environment |  |  |  | 0 | 0%
4.1.3 | Human Resources Organization |  |  |  | 0 | 0%
4.2 | Automated Testing |  |  |  | 0 | 0%
4.3 | Weekly Report |  |  |  | 0 | 0%